## Sheet1
Cluster Upcoming variants
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Fact is affected a project | Remarks
1 | GUI/Sparklet-C++ (OOP) | Aarti B | Training Completed (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development
2 | Collect R_CAR/BeagleBone & Demo Code | Aarti B | Starter Kit to be collected for RCAR, and Reference Design for RH850 from Pratik, Send reminder with video & image | Open | Support TFT Cluster (Infotainment System) Development
3 | RTOS & Linux | Aarti B | Training Completed (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development
4 | IOT (Web Tech) | Aarti B | Training Completed (Code Shared) | Open | Support IOT (ESP) Development
5 | 5" Color LCD to be finalised for scooter segment. | Avinash sir, Mangesh sir | Drawing need to prepare for LCD & Backlite after finalizing | Open | Customer needs + Analyse Market Requirement | 2023-07-28
6 | CAN & EEL Code (Study RL78 Datasheet) | Aarti B | Training Completed (Code Shared) | Open | Product Support
7 | RCA(Supplier MegaEmbedded), H/W Pending Tasks, Marketing (8-Customers ), Color LCD Purchase | Aarti B | Seperate MIS for Embedded Software - Management Information Systems Report , Issues - Required Manpower(PCB Design Engineer) | Open | Product Support | 2023-10-22
Hardware
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Fact is affected a project | Remarks
1 | Hardware design in accordance with safety protocols, and ensure ISO26262 compliance. | Swapnil sir | Dependent Failure Analysis (DFA) as per ISO26262, ISO26262 Output work docs, Validation, FMEA etc. for PCB & Components | Open | Avoid Business Loss due to returns(field failure) & rejections | 2023-04-20 | Pending for 6 month |  | Customer faces issue
2 | Cluster DC-DC issues (Isolated vs Nonisolated) | Swapnil sir | Test DC-DC fluctuations for spike, surge, ripple, reverse polarity etc.. | Overdue |  | 2022-10-04 | Pending for 1 year |  | Customer faces issue
3 | BOM vs all the components to be matrixed for life cycle considering warranty defined for 3 Years | Swapnil sir, Purchase | Datasheet to be shared by purchase team for life cycle calculation, Component variations to be intimated to concerned teams | Open |  | 2023-07-28 | Pending for 3 month |  | There is not proper communication for customer
4 | Root Cause Analysis (RCA) of ODO/TRIP Switch shorting (PCB Right side - Via Coating) & MCU failure (DC-DC Ripple at RBS & deceleration) | Swapnil sir | Cluster DC-DC issues (Isolated vs Nonisolated) & PCB Design (ODO/TRIP Switch) | Open |  | 2023-08-21 | Pending for 2 month |  | Customer faces issue
5 | Sunlit Power Private Limited - Development test jig setup | Swapnil sir, Pramod sir | Need BMS, MCU & Motor for further processing. | Open | R&D | 2023-09-16 | Pending for 1 month |  | There is not proper communication for customer
6 | Bluetooth communication for cluster | Swapnil sir | PCB Design | Open | Customer's need | 2023-07-27 | Pending for 3 month |  | There is not proper communication for customer
7 | MCU Price reduction | Swapnil sir, Purchase | Selection of low-pin MCUs with a single CAN , PCB Modification & Testing, Procure Samples | Overdue | Market competition | 2022-11-24 | Pending for 11 month |  | There is not proper communication for customer
8 | Warning buzzer | Swapnil sir, Purchase | Procure Samples, Adding buzzer inside cluster & Testing | Open | Customer's need + Safety | 2023-05-17 | Pending for 5 month |  | There is not proper communication for customer