## Software
TFT Cluster (Infotainment System) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal
1 | RTOS | Nadir | FreeRTOS | Closed | Affortability/Price reduction: Opensource/Free tool
2 | LINUX (Device Driver) | Nadir | Stand-alone CAN Controller with SPI Interface | Closed
3 | LINUX (SocketCAN) | Nadir | SocketCAN , Socket Programming | WIP
4 | Widget Toolkit (Qt Creator) | Nadir | GUI/HMI Development, OOP | WIP
IOT (ESP) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal
1 | Local Web Server for displaying UART Data | Nadir | Web Technologies | Closed | Cheaper compared to GSM
2 | Advanced Web Technologies | Nadir | Cloud Server (Google Firebase) | WIP | Affortability/Price reduction: Opensource/Free tool

## Systems
Instrument Cluster Support
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Time to submit
1 | Communicate with the Abzo Motors team. | Dheeraj | Software qualification test, ISO26262 Safety requirements, BMS and MCU issues | Overdue | Create a permeant standard CAN Matrix for PVG | 2023-05-29 | ASAP
2 | Update cluster datasheet | Swapnil, Avinash Sir | Refer Symbols & their Functions shared by Embedded Dept. | Open | Boost Marketing | 2023-09-08 | ASAP
3 | Demontration of Instument Cluster to CFT | Aarti B, Dhanal Sir | Mandatory - BD & QA participation | Open | Improve Marketing & EOL Testing |  | ASAP
4 | CAN & EEL Code (Study RL78 Datasheet) | Aarti B | Training Completed (Code Shared) | Open | Product Support |  | ASAP
Cluster Upcoming variants
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Time to submit
1 | Segmented LCD - electrical spec | Swapnil | Verify the electrical specification of LCD & backlight, and conform weather required 3.3V instead of 5V for adding Bluetooth device | Open | Bluetooth Implimentation (27-Jul-23) | 2023-09-27 | ASAP
2 | Cluster outer shape & 5" Color LCD proposal to be finalised for scooter segment. | Mangesh, Aarti B | 5" Color LCD proposal to be prepared for scooter segment. Various Enclosure & LCD Dimensions proposals to be prepared, Drawing need to be prepare for LCD & Backlite after finalizing | Open | Customer needs + Analyse Market Requirement | 2023-07-28 | ASAP
3 | GUI/QT-C++ (OOP) | Aarti B | Training Completed (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development |  | ASAP
4 | IOT (Web Tech) | Aarti B | Trainee (Code Shared) | Open | Support IOT (ESP) Development |  | ASAP
5 | RTOS & Linux | Aarti B | Trainee (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development |  | ASAP
6 | Demontration of TFT Cluster to CFT | Aarti B. | Training Completed | Open | To collect development inputs for Infotainment System |  | ASAP
7 | Demontration of IOT to CFT | Aarti B. | Training Completed | Open | To collect development inputs for IOT |  | ASAP

## Role
Sr No. | Name of Member | Role | Responsibility
1 | Mr. Nadir k T | 1.R&D of embedded systems. | 1.Vendor coordination.
|  | 2.Conducting tests on the embedded software systems to ensure proper integration. | 2.Liaising with design and engineering teams to ensure process alignment.
|  | 3.Documentation related to software development, technical manuals, and firmware usage. | 3.Interaction with other departments for seamless integration and execution of the project.
4.Developing embedded software and programs.
5.Study of embedded system inputs and preparation of software algorithms.
6.Guiding Embedded Systems team as required.
2 | Miss. Aarti Bansod | 1.Software Testing | 1.Software test on actual product.
|  | 2.Documentation | 2.Documentation creation of product.

## Project Status
Sr. No. | Projects | Work Description | Status
1 | TFT Cluster | Linux OS Virtual | Done
|  | CAN Device Driver, Socket Programming | Done
|  | RTOS | Done
|  | LINUX (CAN Interface) | Done
|  | LINUX (Device Driver) | Done
|  | LINUX (Widget Toolkit) | Done
|  | CLI Application | Done
2 | IOT (ESP) Development | Local Web Server for displaying UART Data | Done