## Software
TFT Cluster (Infotainment System) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal
1 | RTOS | Nadir | FreeRTOS | Closed | Affortability/Price reduction: Opensource/Free tool
2 | LINUX (Device Driver) | Nadir | Stand-alone CAN Controller with SPI Interface | Closed
3 | LINUX (SocketCAN) | Nadir | SocketCAN , Socket Programming | WIP
4 | Widget Toolkit (Qt Creator) | Nadir | GUI/HMI Development, OOP | WIP
IOT (ESP) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal
1 | Local Web Server for displaying UART Data | Nadir | Web Technologies | Closed | Cheaper compared to GSM
2 | Advanced Web Technologies | Nadir | Cloud Server (Google Firebase) | WIP | Affortability/Price reduction: Opensource/Free tool

## Systems
Cluster Upcoming variants
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Time to submit
1 | GUI/Sparklet-C++ (OOP) | Aarti B | Training Completed (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development |  | ASAP
2 | Collect R_CAR/BeagleBone & RH850 | Aarti B | Starter Kit to be collected for RCAR, and Reference Design for RH850 from Pratik | Open | Support TFT Cluster (Infotainment System) Development |  | ASAP
3 | Demontration of TFT Cluster to CFT & Pratik | Aarti B. | Training Completed | Open | To collect development inputs for Infotainment System |  | ASAP
4 | RTOS & Linux | Aarti B | Trainee (Code Shared) | Open | Support TFT Cluster (Infotainment System) Development |  | ASAP
5 | IOT (Web Tech) | Aarti B | Trainee (Code Shared) | Open | Support IOT (ESP) Development |  | ASAP
6 | Demontration of IOT to CFT | Aarti B. | Training Completed | Open | To collect development inputs for IOT |  | ASAP
7 | Segmented LCD - electrical spec | Swapnil | Clarify the rationale behind operating the cluster at 5V? as it can be configured to 3.3V. | Open | Bluetooth Implimentation | 2023-07-27 | ASAP
8 | 5" Color LCD to be finalised for scooter segment. | Avinash sir, Mangesh | Drawing need to prepare for LCD & Backlite after finalizing | Open | Customer needs + Analyse Market Requirement | 2023-07-28 | ASAP
9 | Update Color LCD Dwawing for bike segment. | Avinash sir, Mangesh | Update LCD Dwawing with the finalized segment colors to share with our supplier | Open | Bike segment Color LCD Demo for Marketing
Instrument Cluster Support
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Time to submit
1 | CAN & EEL Code (Study RL78 Datasheet) | Aarti B | Training Completed (Code Shared) | Open | Product Support |  | ASAP
2 | Explain the cluster symbols, their respective functions, and the electrical specifications to the CFT team | Swapnil, Aarti B | Mandatory - BD & QA participation | Open | Improve Marketing & EOL Testing |  | ASAP
3 | Communicate with the Abzo Motors team. | Dheeraj | Software qualification test, ISO26262 Safety requirements(Ready Symbol), BMS and MCU issues | Overdue | Create a permeant standard CAN Matrix for PVG | 2023-05-29 | ASAP

## TODO
Task | Date | Time to submit
Binary Sequence |  | 17:00
Macros(#define) |  | 17:00

## Role
Sr No. | Name of Member | Role | Responsibility
1 | Mr. Nadir k T | 1.R&D of embedded systems. | 1.Vendor coordination.
|  | 2.Conducting tests on the embedded software systems to ensure proper integration. | 2.Liaising with design and engineering teams to ensure process alignment.
|  | 3.Documentation related to software development, technical manuals, and firmware usage. | 3.Interaction with other departments for seamless integration and execution of the project.
4.Developing embedded software and programs.
5.Study of embedded system inputs and preparation of software algorithms.
6.Guiding Embedded Systems team as required.
2 | Miss. Aarti Bansod | 1.Software Testing | 1.Software test on actual product.
|  | 2.Documentation | 2.Documentation creation of product.

## Project Status
Sr. No. | Projects | Work Description | Status
1 | TFT Cluster | Linux OS Virtual | Done
|  | CAN Device Driver, Socket Programming | Done
|  | RTOS | Done
|  | LINUX (CAN Interface) | Done
|  | LINUX (Device Driver) | Done
|  | LINUX (Widget Toolkit) | Done
|  | CLI Application | Done
2 | IOT (ESP) Development | Local Web Server for displaying UART Data | Done