## MIS Report
Cluster Upcoming variants
Sr. No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Factors Affecting Project | Remarks
1 | 5" Color LCD to be finalised for scooter segment. | Avinash sir, Mangesh | Drawing need to prepare for LCD & Backlite after finalizing, Pending Inputs from marketting | Open | Customer needs + Analyse Market Requirement | 2023-07-28 | Pending for 3 month | _ | _
Hardware
Sr. No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Factors Affecting Project | Remarks
1 | Hardware design in accordance with safety protocols, and ensure ISO26262 compliance. | Swapnil sir | Dependent Failure Analysis (DFA) as per ISO26262, ISO26262 Output work docs, Validation, FMEA etc. for PCB & Components | Open | Avoid Business Loss due to returns(field failure) & rejections | 2023-04-20 | Pending for 6 month | Quality standards. | Customer faces issue
2 | Cluster DC-DC issues (Isolated vs Nonisolated) | Swapnil sir | Test DC-DC fluctuations for spike, surge, ripple, reverse polarity etc.. | Overdue |  | 2022-10-04 | Pending for 1 year | Product standards | Customer faces issue
3 | BOM vs all the components to be matrixed for life cycle considering warranty defined for 3 Years | Swapnil sir, Purchase | Datasheet to be shared by purchase team for life cycle calculation, Component variations to be intimated to concerned teams | Open |  | 2023-07-28 | Pending for 3 month | Quality standards | There is not proper communication for customer
4 | Root Cause Analysis (RCA) of ODO/TRIP Switch shorting (PCB Right side - Via Coating) & MCU failure (DC-DC Ripple at RBS & deceleration) | Swapnil sir | Cluster DC-DC issues (Isolated vs Nonisolated) & PCB Design (ODO/TRIP Switch) | Open |  | 2023-08-21 | Pending for 2 month | Risk tolerance | Customer faces issue
5 | Bluetooth communication for cluster | Swapnil sir | PCB Design | Open | Customer's need | 2023-07-27 | Pending for 3 month | Product standards | There is not proper communication for customer
6 | MCU Price reduction | Swapnil sir, Purchase | Selection of low-pin MCUs with a single CAN , PCB Modification & Testing, Procure Samples | Overdue | Market competition | 2022-11-24 | Pending for 11 month | Product price reduction | There is not proper communication for customer
7 | Warning buzzer | Swapnil sir, Purchase | Procure Samples, Adding buzzer inside cluster & Testing | Open | Customer's need + Safety | 2023-05-17 | Pending for 5 month | Product standards | There is not proper communication for customer
Quality
Sr. No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Factors Affecting Project | Remarks
1 | Functional testing setup for mass production. | QA (Quality Assurance) professionals | Determine the test requirements, Design the test setup, Develop the test procedures (including SOPs and work instructions), Train the production staff, Monitor the test results. | Open | Improve product's functional safety, Avoid Business Loss due to returns(field failure) & rejections | 2023-05-03 | Pending for 5 month | Risk tolerance | There is not proper communication for customer
2 | S/W Validation Testing & Documentation | Samadhan, Dheeraj | Conduct Qualification tests, compose Test Plans.Evaluate software quality and readiness.Obtain client acceptance and sign-off.Conduct tests in collaboration with clients and customer representatives.Include system testing & acceptance testing.Software Safety Requirement (SSR) verification as per ISO 26262 standard and vehicle-level environment.Hardware in Loop (HIL) Testingvv | Open |  | 2023-06-23 | Pending for 5 month | Risk tolerance | There is not proper communication for customer & Customer faces issue
3 | IATF Internal Audit (Software Development) | Samadhan | IATF16949 - 8.3.2.3 (Development of products with embedded software) | Open |  | 2023-07-10 | Pending for 5 month | Product standards | _
4 | Analysis of rejection | QA (Quality Assurance) professionals |  | Open |  | 2023-09-25 | Pending for 5 month | Product standards | Customer faces issue
Business Development Team
Sr. No. | Activity Description | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Factors Affecting Project | Remarks
1 | ABZO Motors (Ronald fernandez) - Clarify the condition for ready symbol | Dheeraj sir | READY symbol condition in discussion with EMF. Once updated firmware received ABZO will share with PVG in connection. | Overdue | Create a permeant standard CAN Matrix for PVG | 2023-05-29 | Pending for 5 month | Product standards | There is not proper communication for customer
2 | Test bench to be repaired with the help of ABZO Motors | Dheeraj sir | Communicate with ABZO team | Open | Production Inspection 100%, R&D | 2023-08-28 | Pending for 2 month | Resource availability & Risk tolerance | Delay in project
3 | Cluster - Bluetooth Feature data matrix | Dheeraj sir | Communicate with the customer to provide the Bluetooth feature data matrix based on the input CAN database (Format) | Open | Customer's need, much cheaper compared to IOT | 2023-08-18 | Pending for 2 month | Resource availability | Delay in project
4 | BGAUSS - Collect BGAUSS Firmware & Working Cluster Sample | Dheeraj sir | Design PCB & LCD as per the sample | Open | Reduced R&D Timeline, chance for future improvements | 2023-07-28 | Pending for 2 month | Resource availability | Delay in project
5 | Multi-Colour Segmented Display for Cluster (EV) | Dheeraj, Pramod | Select the cluster symbol colours based on market requirement and update current symbols if necessary | Open | Analyse Market Requirement, | 2023-07-28 | Pending for 3 month | Resource availability | Delay in project
6 | LCD Coloured segment - Need to check feasibility with existing supplier | Purchase | Communicate with RK Team based upon market requirement analysis (LCD Colour) done by BD Team | Open | Price negotiation | 2023-07-28 | Pending for 3 month | Resource availability | Delay in project
7 | Share Updated datasheet to BD to explain the cluster functions to the customer | Dheeraj sir, Pramod sir, Swapnil sir | Advantages of PVG cluster compared to similar products | Open | Product marketing based on differentiation | 2023-07-28 | Pending for 2 month | Resource availability | Delay in project
Customer List
Sr. No. | Customer Name | Responsibility | Scope of Action | Status | Goal | Date | Abnormality | Factors Affecting Project | Remarks
1 | ABZO Motors (Ronald fernandez) - Clarify the condition for ready symbol | Dheeraj sir | READY symbol condition in discussion with EMF. Once updated firmware received ABZO will share with PVG in connection. | Overdue | Create a permeant standard CAN Matrix for PVG | 2023-05-29 | Pending for 5 month | Resource availability | Delay in project
2 | BGAUSS - Collect BGAUSS Firmware & Working Cluster Sample | Dheeraj sir | Design PCB & LCD as per the sample | Open | Reduced R&D Timeline, chance for future improvements | 2023-07-28 | Pending for 2 month | Resource availability | Delay in project
3 | Automobile (Ravishankar Kasthuri) - Verify CAN matrix for Automobile with the motor controller vendorfor any required changes | Dheeraj sir |  | Open
4 | ARENQ (Vishnu. V) | Pramod sir |  | Open
5 | REVELEC (Shuhaib) - cluster development | Dheeraj sir |  | Open
6 | CAL on (DOL Mobility) - Technical Solutions: DOL mobility | Pramod sir and Dheeraj sir |  | Open
7 | Prestrogen | Pramod sir |  | Open
8 | Sunlit Power Private Limited - Development test jig setup | Swapnil sir, Pramod sir | Need BMS, MCU & Motor for further processing. | Open | R&D | 2023-09-16 | Pending for 1 month | Resource availability | Delay in project
TFT Cluster (Infotainment System) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Status
1 | RTOS | Nadir | FreeRTOS | Closed | Closed
2 | LINUX (Device Driver) | Nadir | Stand-alone CAN Controller with SPI Interface | Closed | Closed
3 | LINUX (SocketCAN) | Nadir | SocketCAN , Socket Programming | WIP | WIP
4 | Widget Toolkit (Qt Creator) | Nadir | GUI/HMI Development, OOP | WIP | WIP
IOT (ESP) Development
Sr.No. | Activity Description | Responsibility | Scope of Action | Status | Goal
1 | Local Web Server for displaying UART Data | Nadir | Web Technologies | Closed | Cheaper compared to GSM
2 | Advanced Web Technologies | Nadir | Cloud Server (Google Firebase) | WIP | Affortability/Price reduction: Opensource/Free tool

## MIS
https://www.javatpoint.com/mis-report-in-excel
https://www.upgrad.com/blog/what-is-excel-mis-report/
https://www.exceldemy.com/prepare-mis-report-in-excel/
https://www.iso-ne.com/markets-operations/settlements/understand-bill/reports-descriptions
https://www.simplilearn.com/tutorials/excel-tutorial/excel-mis-report

## Project Status
Sr. No. | Projects | Work Description | Status
1 | TFT Cluster | Linux OS Virtual | Done
|  | CAN Device Driver, Socket Programming | Done
|  | RTOS | Done
|  | LINUX (CAN Interface) | Done
|  | LINUX (Device Driver) | Done
|  | LINUX (Widget Toolkit) | Done
|  | CLI Application | Done
2 | IOT (ESP) Development | Local Web Server for displaying UART Data | Done

## Role
Sr No. | Name of Member | Role | Responsibility
1 | Mr. Nadir k T | 1.R&D of embedded systems. | 1.Vendor coordination.
|  | 2.Conducting tests on the embedded software systems to ensure proper integration. | 2.Liaising with design and engineering teams to ensure process alignment.
|  | 3.Documentation related to software development, technical manuals, and firmware usage. | 3.Interaction with other departments for seamless integration and execution of the project.
4.Developing embedded software and programs.
5.Study of embedded system inputs and preparation of software algorithms.
6.Guiding Embedded Systems team as required.
2 | Miss. Aarti Bansod | 1.Software Testing | 1.Software test on actual product.
|  | 2.Documentation | 2.Documentation creation of product.